## Tracker
Marlowe Atelier · Sample Tracking Log — SS26
Season ref: SS26 / Spring-Summer · Critical path vs Calendar targets · As of 15 Jul 2026
Style # | Style Name | Category | Proto 1 |  | Proto 2/SMS |  | Fit Sample |  | PP Sample |  | Gold Seal |  | Current Stage | Days in Stage | On Track?
|  |  | Status | Date | Status | Date | Status | Date | Status | Date | Status | Date
SS-101 | Marlowe Slip Dress | Dresses | Approved | 2026-04-20 | Approved | 2026-05-08 | Approved | 2026-05-26 | Approved | 2026-06-12 | Approved | 2026-07-02 | Gold Seal | 13 | complete
SS-102 | Colette Blouse | Tops | Approved | 2026-04-22 | Approved | 2026-05-11 | Approved | 2026-05-28 | Approved | 2026-06-15 | Approved | 2026-07-06 | Gold Seal | 9 | complete
SS-103 | Aubrey Trench | Outerwear | Approved | 2026-04-18 | Approved | 2026-05-06 | Approved | 2026-05-22 | Approved | 2026-06-09 | Approved | 2026-07-09 | Gold Seal | 6 | complete
SS-104 | Verity Wrap Dress | Dresses | Approved | 2026-04-24 | Approved | 2026-05-14 | Approved | 2026-06-01 | Approved | 2026-06-20 | In Progress | 2026-07-10 | PP Sample | 5 | on track
SS-105 | Odile Knit | Knitwear | Approved | 2026-04-25 | Approved | 2026-05-15 | Approved | 2026-06-03 | Approved | 2026-06-22 | Not Started |  | PP Sample | 23 | on track
SS-106 | Sévigné Blazer | Tailoring | Approved | 2026-04-27 | Approved | 2026-05-18 | Approved | 2026-06-05 | In Progress | 2026-06-28 | Not Started |  | Fit Sample | 17 | DUE/LATE
SS-107 | Lisette Midi Skirt | Skirts | Approved | 2026-04-28 | Approved | 2026-05-20 | Approved | 2026-06-08 | Not Started |  | Not Started |  | Fit Sample | 37 | DUE/LATE
SS-108 | Margaux Trouser | Trousers | Approved | 2026-04-29 | Approved | 2026-05-22 | In Progress | 2026-06-26 | Not Started |  | Not Started |  | Proto 2/SMS | 19 | DUE/LATE
SS-109 | Delphine Camisole | Tops | Approved | 2026-05-02 | Approved | 2026-05-25 | Approved | 2026-06-10 | Not Started |  | Not Started |  | Fit Sample | 35 | DUE/LATE
SS-110 | Ines Shirt Dress | Dresses | Approved | 2026-05-04 | Approved | 2026-05-28 | Not Started |  | Not Started |  | Not Started |  | Proto 2/SMS | 48 | DUE/LATE
SS-111 | Bardot Cardigan | Knitwear | Approved | 2026-05-06 | In Progress | 2026-06-12 | Not Started |  | Not Started |  | Not Started |  | Proto 1 | 33 | DUE/LATE
SS-112 | Solene Tailored Vest | Tailoring | Approved | 2026-05-08 | In Progress | 2026-06-10 | Not Started |  | Not Started |  | Not Started |  | Proto 1 | 35 | DUE/LATE
SS-113 | Romy Pleated Skirt | Skirts | Approved | 2026-05-09 | In Progress | 2026-06-14 | Not Started |  | Not Started |  | Not Started |  | Proto 1 | 31 | DUE/LATE
SS-114 | Estelle Wide Trouser | Trousers | Approved | 2026-05-11 | In Progress | 2026-06-16 | Not Started |  | Not Started |  | Not Started |  | Proto 1 | 29 | DUE/LATE
SS-115 | Juno Denim Jacket | Denim | Approved | 2026-05-12 | Rejected | 2026-06-18 | Not Started |  | Not Started |  | Not Started |  | Proto 1 | 27 | DUE/LATE
SS-116 | Cleo Silk Top | Tops | Approved | 2026-05-14 | In Progress | 2026-07-06 | Not Started |  | Not Started |  | Not Started |  | Proto 1 | 9 | DUE/LATE
SS-117 | Farah Maxi Dress | Dresses | Approved | 2026-05-16 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Proto 1 | 60 | DUE/LATE
SS-118 | Noor Knit Dress | Knitwear | In Progress | 2026-07-08 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | 7 | DUE/LATE
SS-119 | Thea Culotte | Trousers | Approved | 2026-05-05 | Approved | 2026-05-30 | Rejected | 2026-06-24 | Not Started |  | Not Started |  | Proto 2/SMS | 21 | DUE/LATE
SS-120 | Wren Overshirt | Outerwear | Approved | 2026-05-18 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Proto 1 | 58 | DUE/LATE
PIPELINE FUNNEL — samples approved through each gate | [12 empty] | As of 15-Jul-2026
Gate | Approved | Funnel
Proto 1 | 19 | 19
Proto 2/SMS | 11 | 11
Fit Sample | 8 | 8
PP Sample | 5 | 5
Gold Seal | 3 | 3
Rejected |  | 2
Overdue (ageing > 21d) |  | 11
Due / Late vs calendar |  | 15
Formulas:
Days in Stage = IFERROR(IF(MAX([Date],[Date],[Date],[Date],[Date])=0,"",TODAY()-MAX([Date],[Date],[Date],[Date],[Date])),"")

## Calendar
Marlowe Atelier · SS26 Critical-Path Calendar
Gate target dates drive the Tracker's On Track? / DUE-LATE flags via cross-sheet lookup.
Gate | Target Date | Lead Days | Owner | Notes
Proto 1 | 2026-05-01 | 14 | Design / Studio | First proto off the block; silhouette sign-off.
Proto 2/SMS | 2026-05-25 | 24 | Product Dev | Salesman sample / showroom-ready make.
Fit Sample | 2026-06-15 | 21 | Technical / Fit | Graded fit session on the base size.
PP Sample | 2026-07-05 | 20 | Production | Pre-production seal on bulk fabric & trims.
Gold Seal | 2026-07-20 | 15 | QA / Merch | Final gold seal — release to bulk.
Note on B5: Critical-path anchor: Proto 1 sign-off gates the whole SS26 make. Each downstream target = prior target + lead days; slipping this pushes every gate.

## Notes
Marlowe Atelier · SS26 Rejection & Risk Notes
Rejected gates and at-risk (stuck) styles — reason, corrective action, and re-submit plan.
Style # | Style Name | Gate | Rejection / Risk Reason | Action | Re-submit
SS-115 | Juno Denim Jacket | Proto 2/SMS | Colour lab-dip #3 failed — indigo off vs standard (ΔE 2.4). | Re-dip against approved swatch; supplier to hold bulk. | 2026-07-24
SS-119 | Thea Culotte | Fit Sample | Armhole binding puckering; sleeve pitch rotated on base size. | Re-cut binding, re-walk sleeve; new fit sample. | 2026-07-22
SS-111 | Bardot Cardigan | Proto 2/SMS | SMS stalled 30d+ — mill yarn delay on the rib. | Chase mill ETA; consider substitute yarn if >1 wk. | 2026-07-21
SS-112 | Solene Tailored Vest | Proto 2/SMS | Hand-feel off vs standard on the melton; pressing marks. | Re-make with corrected press; QA hand-feel check. | 2026-07-20
SS-113 | Romy Pleated Skirt | Proto 2/SMS | Pleat depth inconsistent across the run. | Re-set pleater; confirm depth spec on tech pack. | 2026-07-23
SS-114 | Estelle Wide Trouser | Proto 2/SMS | Waistband roll on the wide-leg; interfacing too soft. | Swap to firmer fusible; re-make SMS. | 2026-07-25