## T&A — Main body
CORVEAU STUDIO — SS26 · Time & Action Calendar — Main body
Milestone | Owner | Planned | Revised | Actual | Status | Late flag | Dependency | Notes | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | start_wk | end_wk
Proto approval | Product Dev — L. Moreau | 2026-05-12 |  | 2026-05-13 | Complete |  | — | Silhouette signed off | [10 empty] | 20 | 20
Fit approval | Product Dev — L. Moreau | 2026-05-19 |  | 2026-05-21 | Complete |  | Proto approval | Grade rules locked | [10 empty] | 21 | 21
PP sample | Product Dev — L. Moreau | 2026-05-27 | 2026-05-28 | 2026-05-29 | Complete |  | Fit approval | Pre-production seal | [10 empty] | 22 | 22
Fabric in | Sourcing — T. Okafor | 2026-06-02 |  | 2026-06-03 | Complete |  | PP sample | Main body twill, 1,850m | [10 empty] | 22 | 23
Trims in | Sourcing — T. Okafor | 2026-06-09 |  | 2026-06-10 | Complete |  | Fabric in | Zips, labels, hangtags | [10 empty] | 23 | 24
Bulk cut | Factory Cutting — R. Delacroix | 2026-06-16 |  | 2026-06-17 | Complete |  | Trims in | Lay planned 62 plies | [10 empty] | 24 | 25
Sew start | Factory Sewing — R. Delacroix | 2026-06-23 |  | 2026-06-24 | Complete |  | Bulk cut | Line 1 + Line 2 | [10 empty] | 25 | 26
Finishing | Quality — S. Batra | 2026-06-30 |  | 2026-07-02 | Complete |  | Sew start | Press, tack, tag | [10 empty] | 26 | 27
QC | Quality — S. Batra | 2026-07-08 | 2026-07-16 |  | Delayed |  | Finishing | AQL 2.5 — recovery re-plan | [10 empty] | 27 | 28
★ Ex-factory | Logistics — M. Haddad |  |  |  | In progress |  | QC | Goods leave plant | [10 empty] | 28 | 29
ETD (vessel departs) | Logistics — M. Haddad |  |  |  | Not started |  | ★ Ex-factory | Booking CRV-SS26-001 | [10 empty] | 29 | 29
Warehouse in | Logistics — M. Haddad | 2026-07-20 |  |  | Not started |  | ETD (vessel departs) | EU DC receipt | [10 empty] | 29 | 29
Late milestones (auto):
Program window: W20–W29 · SS26
Formulas:
Late flag = IF(AND([Actual]="",TODAY()>[Planned]),TEXT(TODAY()-[Planned],"0")&"d late","")
Note on C3: Planned dates = Corveau Studio SS26 critical path (illustrative template).
Note on A11: Planned window (08-Jul) overlaps 'Factory Summer Maintenance' shutdown (06–08 Jul, see Holidays) — QC start slipped; currently late.
Note on C12: Cross-sheet: Vessel ETD (Holidays) minus ex-factory→port lead.

## T&A — Knits
CORVEAU STUDIO — SS26 · Time & Action Calendar — Knits program
Milestone | Owner | Planned | Revised | Actual | Status | Late flag | Dependency | Notes | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | start_wk | end_wk
Yarn approval | Sourcing — T. Okafor | 2026-06-02 |  | 2026-06-03 | Complete |  | — | Merino 12gg, 640kg | [10 empty] | 23 | 23
Knit-down approval | Product Dev — L. Moreau | 2026-06-09 |  | 2026-06-10 | Complete |  | Yarn approval | Stitch/gauge signed | [10 empty] | 23 | 24
Fit approval | Product Dev — L. Moreau | 2026-06-16 |  | 2026-06-18 | Complete |  | Knit-down approval | Body block locked | [10 empty] | 24 | 25
PP sample | Product Dev — L. Moreau | 2026-06-24 | 2026-06-25 | 2026-06-26 | Complete |  | Fit approval | PP seal — knits | [10 empty] | 25 | 26
Panel knitting | Factory Cutting — R. Delacroix | 2026-06-30 |  | 2026-07-01 | Complete |  | PP sample | 18 machines allocated | [10 empty] | 26 | 27
Linking & finishing | Factory Sewing — R. Delacroix | 2026-07-07 |  | 2026-07-09 | In progress |  | Panel knitting | Linking + wash + press | [10 empty] | 27 | 28
QC | Quality — S. Batra | 2026-07-16 |  |  | Not started |  | Linking & finishing | AQL 2.5 knit defects | [10 empty] | 28 | 29
★ Ex-factory | Logistics — M. Haddad | 2026-07-18 |  |  | Not started |  | QC | Consolidate with main body | [10 empty] | 29 | 29
Late milestones (auto):
Formulas:
Late flag = IF(AND([Actual]="",TODAY()>[Planned]),TEXT(TODAY()-[Planned],"0")&"d late","")
Note on C3: Knits critical path offset ~3 weeks behind main body (SS26 template).

## Capacity
CORVEAU STUDIO — SS26 · Weekly line capacity vs booked load
Metric | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
Line 1 — Capacity (units) | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
Line 1 — Booked (units) | 900 | 1200 | 1500 | 1700 | 2200 | 2000 | 1850 | 1600 | 1200 | 800
Line 1 — Utilisation
Line 2 — Capacity (units) | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
Line 2 — Booked (units) | 600 | 800 | 1100 | 1350 | 1450 | 1500 | 1400 | 1250 | 950 | 600
Line 2 — Utilisation
Plant — Utilisation (booked/cap)
Note on B3: Line 1 nominal weekly stitching capacity (units) — plant standard.
Note on F4: W24 load exceeds capacity — overbooked, see red flag.

## Holidays
CORVEAU STUDIO — SS26 · Factory holidays & logistics reference
Holiday / closure | Start | End | Working days lost
Labour Day break | 2026-03-02 | 2026-03-04
Dragon Boat Festival | 2026-06-17 | 2026-06-19
Factory Summer Maintenance | 2026-07-06 | 2026-07-08
LOGISTICS REFERENCE
Vessel | MV Corveau Star
Vessel ETD (port depart) | 2026-07-17
Port of loading | Ningbo, CN
Transit days (sea) | 24
Ex-factory→port lead (d) | 2
Est. warehouse-in (EU DC)
Formulas:
Working days lost = NETWORKDAYS([Start],[End])
Note on A5: Overlaps Main-body QC planned window — driver of the QC slip.
Note on B10: Vessel ETD — drives Main-body ★ Ex-factory & ETD (cross-sheet).
Note on B13: Factory→port lead used by ★ Ex-factory planned date.